## Consolidated - Tech and comm
ITER-India (IPR) response to Pre-bid queries - Tender No. I-ITN19002 dated 12th June 2019
Sr. No. | Ref. Tender Part / Section No. | Ref. Clause No. | Description of the query | Response of ITER-India
1 | Section 3 PRICE BID Foramt-Table -2 | serial no.8 of the table | Supervision Charges for Final Acceptance Test at ITER Site, France. In the price bid format maximum supervision charges for 8 weeks is given. Pls. define the scope of the supervision activities. Pls. calrify if the supervision period is extended by ITER India/ITER Organization (IO) , how the contractor will be compensated. | Scope of work is define in 3.3.2 of APB3_11 and refer note no. 4 in the price bid format Section C. Payment of supervision will be on actual utlization of supervision activity on per day basis. Per day rate will be derived based on the rate quoted by the bidder in sr. no. 8 of Table-2 of price bid format.
2 | Section 3 Table -3 Commercial terms and conditions |  | Delivery -FCA Contractors's premises- Transportation , insurance from factory to final destination ITER-Site shall be in the scope of ITER-India. Pls. confirm | confirmed
3 | PART A II-Delivery Schedule | Table no.1 | Material receipt period and mock up TCPH period are same (T0 + 6 Months). Unless the mock up is approved by ITER India , manufacturing of TCPH cannot be started. Pls. calrify the period between receipt of materials and TCPH mock up. Pls. clarify | Mock-up and material procurement can be carried out in parallel. Manufacturing of TCPH can be initiated after the approval of Mock-up. Schedule activities as per sr. no. 3,4 and 5 are changed to 9 months as per attached amendment.
4 | PART A II-Payment Schedule | 1.7.4.2.4 | The validity of advance payment Bank Guarantee (BG) should remain valid till 60 days beyond the last delivery in the bid documents. Bidder requests for BGs to be released on pro rata basis. Pls. confirm | ABG to release on site acceptance of 02 TCPHs(02 ABGs - one for 02 TCPH and another for 04 TPCH). Refer amendment for more details
5 |  | 1.6.1.3 | Security Deposit 10% of the Contract value- The BG shall remain valid till expiry of 60 days from the date Final site acceptance of delivered items. If needed arises, the Contractor shall extend the validity of the BG for suitable period at his expenses.- Pls. confirm the latest date to which extension will be required. | Latest date of BG validity is 39 months from the LoI date
6 |  | 1.6.2.1 and 1.6.2.2 | PBG 10% will be effective fro the date of site/Final acceptance and shall remain in force two months beyond the Warranty period mentioned in the tender documents. In the event of BG needs extension, the Contract shall extend the validity of PBG for suitable period at his expenses.e Contractor's expenses- - Pls. confirm the latest date to which extension will be required. | Latest date will be two months beyond the warranty period i.e. 03 years from the date of delivery or 2 years from the date of final acceptance, whichever is earlier
7 |  | 1.6.3 | All Bank Charges, if applicable shall be borne by the Contractor only. Clarification is required for schedule delayed by ITER India/ITER Organization (IO) | BGs has to be extended on an immeddiate basis by the contractor on request of the Purchaser. Such bank charges for extended period of BGs shall be reimbursed on actual basis against valid documentary proof for the period of delay attributed to the Purchaser. Refer amendment for details
8 |  | 1.7.1 | Terms of Prices- The unit prices for this Contract shall be firm during the validity and extended validity of the Contract. No price variation is applicable on contract price/contract value. Pls. clarify if the schedule only (dispatch, FAC) is extended by ITER India/IO , the price shall be according to the "Change Management" clause 1.21 of the tender documents. | The price shall not be in accordance with the change management. There is no price change applcable for schedule extension
9 |  | 1.13.1 | Rejection of defective goods and Contractor's Liability- If packing is damaged due to transporter no liability on the Contractor. We will provide accelerometer on frame. Pls. confirm | Refer cl no. 1.13.1.2 of Tender section A(II) which mentions the damages due to Purchaser
10 |  | 1.21.2 | Any changes originating from the Purchaser including reduction of scope of supply of TCPH shall be governed by "Change Management" | In case of any unit rate of item(s) is available or agreed in the contract, same shall be used for addition/deletion purpose
11 | General |  | If the period of Final Acceptance Test (FAT) gets extended by ITER India/ITER Organization (IO) by more than 6 months the payment against FAT milestone shall be paid against PBG. Pls. confirm | We will put in all efforts to carry out Final Acceptance test within 6 months from the date of receipt of items at site. However, if the acceptance test is delayed beyond 6 months then payment against SAT milestone shall be paid against PBG with validity for 36 months plus claim period of 2 months from the date of delivery. Refer amendment for more details
12 | Section-B Technical & management specifications, Scope of Supply and Scope of Work | 1. Introduction | It is mentioned that this is an 'ïn-kind' contribution being executed through the Indian domestic agency called ITER-India. Please confirm the following: 1)Will ITER-India raise an invoice to ITER Organisation (IO) and payment will be remitted to India. 2) Who will be the exporter in shipping bill ? 3) Can supplier (Bidder) be the exporter or third party in the shipping bill ? 4) Can supplier (Bidder) avail export benefits ? | ITER-India (IPR) will be the exporter and no third party allowed. Contractor cannot avail export benefits
13 | Section A-(II): Terms and conditions of contract | 1.7.3.4 | It is mentioned that GST will be extra as applicable at the prevailing rates and in the Pre-bid meeting held on 12th July 2019, it was informed that concessional rate of 5% would be applicable. Please clarify why GST is applicable at all as items are being exported? | items are being exported by ITER-India and not by the Contractor. Hence, as per referred notification in the tender, 5% GST is applicable certificate issued by us
14 | Section C: Price bid format | Table 2 S. No. 8 | It is mentioned in the bid document that Bidder has to furnish weekly supervision charges for Final Acceptance Test at ITER Site, France for 8 weeks. Please clarify the scope of work under above mentioned supervision and what facilities will be provided to supplier's engineers at site by ITER India/France? | Scope of work is define in 3.3.2 of APB3_11. And refer note no. 4 in the price bid format Section C
15 | Section A-(II): Terms and conditions of contract | Table 2-Payment Schedule S.No. 9 | It is mentioned that supervision charges will be paid at actuals. Also supervision charges need to be furnished per week basis. Please clarify what will be the methodology to raise the invoice in case supervision period is only a part of week (not a full week). | Payment of supervision will be on actual utlization of supervision activity on per day basis. Per day rate will be derived based on the rate quoted by the bidder in sr. no. 8 of Table-2 of price bid format.
16 | Section A-(II): Terms and conditions of contract | Annexure-2 Bank Guarantee (Advance Payment) | As per the tender an advance payment guarantee of 10% value of the contract needs to be submitted by the supplier. As per APG format S.No.10 guarantee shall remain in force until two months beyond the delivery of last consignment. If first batch of 2 Nos. TCPH is to be dispatched in 19 months and 2nd batch of 4 Nos in 31 months then please allow pro rata reduction of APG adjusting the despatches. | ABG to release on site acceptance of 02 TCPHs(02 ABGs - one for 02 TCPH and another for 04 TPCH). Refer amendment for more details
17 | Section A-(II): Terms and conditions of contract | 1.19.1.2 (Warranty) | It is mentioned that "The Contractor shall provide a minimum warranty covering repair or replacement of the Items up to 36 months from the date of delivery of all TCPHs (6 nos.) or 24 months from the date of final acceptance of all TCPHs (6 nos.) at ITER Organization, France Site, whichever is earlier." If first batch of 2 Nos. TCPH is to be dispatched in 19 months and 2nd batch of 4 Nos in 31 months then please allow for separate warranty period for 2 Nos & 4 Nos TCPH as applicable. | Refer tender clause 1.6.2.1 fo section -A(II) in which we have already sked for separate PBG for first 02 TCPH and another PBG for last 04 TPCH
18 | Section A-(II): Terms and conditions of contract | 1.6.1 (Security Deposit) | It is mentioned that within three weeks from the date of signing of Contract, the Contractor shall submit an irrevocable Bank Guarantee (BG) equal to 10% of total Contract value as “Security Deposit” towards satisfactory execution and performance of the Contract. The Bank Guarantee shall remain valid till the expiry of (60) sixty days from the date of Final site acceptance of delivered Items under this Contract. If final acceptance of first batch of 2 Nos. TCPH at site by ITER to be done in 24 months and 2nd batch of 4 Nos in 37 months then please allow prorata vacation of Bank Guarantee after Final acceptance of first batch of 2 Nos. TCPH. | Tender terms remains unchanged
19 | Section A-(II): Terms and conditions of contract | 1.6.3 (Bank Charges) | It is mentioned that all bank charges of bank guarantees shall be borne by the Contractor only. Please confirm who will bear the charges of BG extension if delay is attributable to ITER India? | BGs has to be extended on an immeddiate basis by the contractor on request of the Purchaser. Such bank charges for extended period of BGs shall be reimbursed on actual basis against valid documentary proof for the period of delay attributed to the Purchaser. Refer amendment for details
20 | Section A-(II): Terms and conditions of contract | Table 2-Payment Schedule S.No. 7 &10 | It is mentioned that 10% payment will be made after each Final site acceptance of first & second batch of TCPH. As supplier's (Bidder) scope is supply of material upon FCA at factory basis. Please clarify how the timely payment will be ensured when supply is on time and final site acceptance is inordinately delayed by ITER India / ITER Organisation? | We will put in all efforts to carry out Final Acceptance test within 6 months from the date of receipt of items at site. However, if the acceptance test is delayed beyond 6 months then payment against FAT milestone shall be paid against PBG with validity for 36 months plus claim period of 2 months from the date of delivery. Refer amendment for details
21 | Section A(I) | 3.4 Annexure-4 | Bidder shall submit two sets of documents in support of the information provided We will submit two set of bids origional and duplicate so shoudld each bid contains 2 sets of support document or 1 set with each bid woulds suffice | Complete bid documents including supporting documents (i.e part of bid)needs to be submitted in duplicate
22 | Section A(I) | 3.4 A.2 | we have more than one sub-contractor for the same activity,should be submit experience details of all sub-contractors ? We may ultimately settle with one of them only with I-I approval | Yes
23 | Section A(II) | 1.17 INSURANCE | Not clear, may kindly explain during pre-bid meeting | Discussed during pre-bid meeting based on the tender terms
24 | Section-A (II) | 1.2.6.2 | This technical information, drawings, specifications and other related documents shall be returned to the Purchaser in proper condition with all approved copies and duplicates, if any, immediately after they have been used for the agreed purpose. It is difficult to maintain paper copies for a duration more than 4 years. Bidder proposes to destroyed after they have been used for agreed purpose. | During the execution of the Contract, we will provide access to IT system on which the documents can be interchanged and approved documents can be uploaded. One set of approved documents as per the requirement in the contract needs to be submitted to the Purchaser.
25 | Section-A (II) | 1.4.3.4 | During the Contract period, to carry out some activities listed in scope of work using the Purchaser’s workstation (especially using ENOVIA/CATIA software), the Contractor needs to deploy his manpower at the Purchaser’s office at the Contractor’s risk and cost. For this, the Purchaser will not provide any facility except office space, workstation and license to work at ITER-India office and will not provide any local hospitality like lodging, transportation, food, etc. Considering concurrent manufacturing scenario, Bidder proposes to perform engineering activities at Bidder design office which is nearby production shops. Drawings will be submitted in PDF format for approval. CATIA Manufacturing model and drawings will be updated in ENOVIA for reference. | Bidder shall prepare manufacturing drawings in Catia using its own resources, while Enovia work needs to perform at ITER-India office. Drawings can be submited in pdf format. However Bidder shall upload manufacturing model in Enovia. The approval of pdf drawing shall only be provided after enovia model approval.
26 | Section-A (II) | 1.5.1.3 | ITER-India reserves the right to increase or decrease the quantities of work or to totally omit any items of work and the Contractor shall not be entitled to claim any extras of damages on these grounds. We understand that such change management should have mutual consent as it will surely impact our pricing. | In case of any unit rate of item(s) is available or agreed in the contract, same shall be used for addition/deletion purpose
27 | Section-A (II) | 1.7.4.2 | Approval of manufacturing/fabrication drawings by the Purchaser. If work is to be done in ENOVIA at I-I office, Bidder proposes to have at least 1800 working hours in 3 months. | Bidder shall prepare manufacturing drawings in Catia using its own resources, while Enovia work needs to perform at ITER-India office. Refer Sr. No 25 for more detail.
28 | Section-A (II) | 1.7.4.2 | Delivery Schedule: Sr. No. 2 and 5, both are stating approval of manufacturing drawings. In order to meet the tight project schedule, Bidder proposes to have new set of comments from I-I / IO only for twice per drawing/document before approval. No new comment after approval. Bidder also proposes to approve documents/drawings with mutually agreed comments so that manufacturing progresses in parallel of revision of document/drawing. | Completeness of documents and drawings shall be ensured by Bidder. Approval of drawing or docuements does not relieve Bidder from its responsibility.
29 | Section-A (II) | 1.7.4.2 | Delivery Schedule: Sr. No. 5 Deliverables of MRR shall be concluded well in advance. | Refer Sr. No. 61
30 | Section-A (II) | 1.7.4.2 | Delivery Schedule: Sr. No. 9 Considering the material procurement time and mock-up requirement, Bidder suggests delivery period of 24 months. | Refer amendment in delivery schedule for more details
31 | Section-A (II) | 1.19.1 | Warranty: Sunset clause for warranty period is not defined. | Refer amendment for more details
32 | Section-B_Tech&Management_Specs | Table 6 - TCPH Engineering, Material Procurement, Manufacturing,Welding & NDT of welds | Use of higher edition or latest edition of ASME codes instead of specified code edition 2013 is permitted. Please confirm. | Edition shall be followed as per tender
33 | Section-B_Tech&Management_Specs | Section 9.7.2 Bullet 4 | It is stated- "Bellow supplier shall produce a proof-of principle bellows, qualify the design by testing and submit the qualification report to I-I approval" Please confirm 1.Whether the testing is to be performed for both internal and external bellow individually or in assembled condition? 2. What other physical testing is to be carried out apart from pressure testing to qualify the bellow ? Please also confirm the no. of cycles related to testing (if required). 3. Only after the approval of the test report by I-I the manufacturing of actual bellows shall be permitted? | 1. Yes all qualification testings shall be carried out in assembled condition 2. clause 6.2 of APB3_13 shall be followed,and it is requested to clarify the pressure testing method ( Hydraulic or pneumatic) along with defining the sequence of testing in the bellows qualification plan. Spring rate shall be measured in axial direction. 3. Yes, it will be a hold point
34 | II-TCPH-APB3_01_Manufacturing_Requirements/01_Mandatory Appendices/Section-B_Tech-Sepcs | 2. REFERENCE | IGC & impact test are to be considered as mandatory requirement for material. Please confirm | Impact test requirement shall be applicable as per Code requirement. IGC Test shall be considered as a requirement of ASTM 262 Practice E.
35 | II-TCPH-APB3_01_Manufacturing_Requirements/01_Mandatory Appendices/Section-B_Tech-Sepcs | Section 4.2 Bullet 2 | It is stated in Section 4.2 that- " All surface of plate forming vacuum boundary shall be such that vacuum boundary becomes parallel to the rolling direction." For Wall Flanges, (Drawing no. 034344) We would propose to manufacture as per details shown in sketch below. Please confirm whether this is acceptable. | Yes ,shown sketch is acceptable
36 | II-TCPH-APB3_02_Engineering Drawings | Section 3 | ITER-India(I-I) will provide Enovia model at the start of the project, any changes further will be communicated by I-I via change management. Bidder is responsible for uploading only the final model in Enovia. Bidder is not responsible for downloading any data from Enovia. Please confirm our understanding. | There will be no model download from Enovia , Bidder shall update in enovia the manufacturing model after incorporating each change from Bidder and change provided by I-I.
37 | Appendix-II-TCPH-APB 3_03 Welding Requirements | Section 3.2 | It is stated- "Preference is given to automatic or mechanized welding processes as to limit human error. Manual welding process may be used if necessary but its extent shall be minimized." Can the bidder choose manual welding for the entire job. Please confirm. | clarity exist in clause
38 | Appendix-II-TCPH-APB3_07 Leak Testing | Section 3.3.1 Local leak testing ( Individual welds leak test) | Please confirm that the leak testing of two or more welds can be performed together based on the testing feasibility. Further, local leak testing will be performed by evacuating one portion by using temporary isolation and helium shall be sprayed from other side. Please confirm our understanding. | Yes two or more welds can be performed .Fesibility shall be eshtablised and Procedure shall be prepared & approved and validated during Execution.
39 | II-TCPH-APB3_09 Labelling, Cleaning, Packing, Shipping and Handling | Section 5 | It is stated - "The transport fixture designed by the bidder shall be capable to withstand accelerations up to 5 g during transportation from factory to ITER site." Kindly confirm 5g in which directions. Our understanding is that only design of packing i.e. transport frame is in Bidder scope and design and analysis of the frame will be approved by I-I/IO , while TCPH is already designed for 5g by I-I/IO. At reciept of consignement at IO, if the acceleration values exceed 5g ,however there is no damage to the packing then any internal damage caused to equipment shall not be responsibility of bidder as the same has not been designed by bidder. Please confirm our understanding. | Bidder to design fixture capable of withstanding 5g in each direction with TCPH
40 | II-TCPH-APB3_10 _ Engineering Analysis | Section 3 | It is stated- If the design changes are requested by the Bidder,I-I and IO shall assess the design impact. If necessary, Bidder shall perform the FEA analysis as per load specification document. Kindly confirm the definition of design changes. Changes done to make the component suitable for manufacturing is not considered as design change, Please confirm. | Change in structural integrity is a "design change" for this clause.
41 | II-TCPH-APB3_10 _ Engineering Analysis | Section 1 | As TCPH is PIC/SIC-I, Is TCPH model with welds and weld lines to be analysed as per the Load specification document ? Please confirm. | NO analysis is required with welds and weld lines. However analysis is required if there is a change in configuration as per APB3_10.
42 | II-TCPH-APB3_13 Bellows/01_Mandatory Appendices/Section-B_Tech-Sepcs | Table 1 | According to document - RDB3_05 TCPH_System_Load_Specification_P8UMCD_v1_6, Table 19 , the max external pressure on bellow is 0.247MPa where as as per Appendix-II-TCPH-APB3_13 Bellows Table 1 the max external pressure is 0.2 Mpa. Kindly confirm which pressure to be considered. Also confirm that, which document is to be refered for bellow design. | Appendix-II-TCPH-APB3_13 shall be followed Please note Minor change in External pressure as 0.15 Mpa gauge pressure in place of 0.2 Mpa.
43 | II-TCPH-APB3_13 Bellows/01_Mandatory Appendices/Section-B_Tech-Sepcs | Table 1 | Kindly specify the no. of load cylce for design of both internal and external bellow. Is it 1000 or more ? | Min. number of cycles for fatigue life cycle shall be as per load cases mentioned in APB3_13. However Design analysis shall be performed for cumulative fatigue cycles for all load cases. Number of Cycles shall be agreed based on cumulative fatigue may be on single load condition after completion of design.
44 | II-TCPH-APB3_13 Bellows/01_Mandatory Appendices/Section-B_Tech-Sepcs |  | Which temperature out of 200 and 250 °C is to be considered as baking temperature of Bellow? | 200 deg. C shall be considered as per design temprature specified in APB3_13
45 | II-TCPH-APB3_13 Bellows/01_Mandatory Appendices/Section-B_Tech-Sepcs | Table 1 | 500 baking cycle at temperature of 200/250 deg C and with given displacements in table are to be considered for bellow design ? Kindly confirm. | 200 deg C shall be considered for bellow design. Number of Cycles shall be agreed based on cumulative fatigue may be on single load condition after completion of design.
46 | II-TCPH-APB3_13 Bellows/01_Mandatory Appendices/Section-B_Tech-Sepcs | General | Is bellow to be designed for seismic case also? Kindly clarify. | Yes , It is part of load condition mentioned in APB3_13
47 | II-TCPH-APB3_13 Bellows/01_Mandatory Appendices/Section-B_Tech-Sepcs | Setion 6.2 | Kindly provide details like no. of cycles, load condition etc for fatigue testing. | Refer No.43
48 | RDB3_08 Appendix_9_Bellows_2E5LJA_v1_3 | Section 9.6.2 | It is stated- "Type Testing of the bellows assemblies should show no failures at 15 g acceleration after 1000 cycles under the condition specified in 9.6.1" . What kind of analysis/testing is to be performed Kindly confirm. | Mechanical Shock Testing is not required
49 | RDB3_08 Appendix_9_Bellows_2E5LJA_v1_3 | Section 9.6.3 | Fatigue life tests should be performed under load conditions similar to ITER loading condition. Kindly provide details like no. of cycles, load condition etc for fatigue testing. | Refer No.43
50 | Section-B: Technical & management specifications, Scope of Supply and Scope of Work | 9.7.2. Design Documentation Requirements | 1. Please clarify on the format in which 3D models have to be submitted by Bidder for evaluation. | 3D model shall be submitted in CATIA as per requirements of APB3_02. Refer Sr. 25 for more detail.
51 | Mandatory Appendix: II-TCPH-APB3_06 | 3.3. Baking | 1. Please clarify whether baking is to be done for individual components or for assembly alone. 2. Also, there is a mismatch between the baking temperature specified in the specification and the vacuum hand book, appendix-15. Kindly clarify. | there is no requirement to bake the individual component or assembly. Stage of baking is mainly related to the welding activity and the LPE to be performed on the Weld joint . Therefore, instead of defining it as a component stage or assembly stage, it would be appropriate to consider the stage of welding. According to APB3_04, "On welds forming the vacuum boundary, LPE shall be avoided. In case LPE is required to be performed as per code requirement, the Liquid Dye penetrant tested area shall be subsequently baked at T = 200 ºC for a minimum of 24 hours prior to vacuum leak testing since the TCPH is VQC1A components (RDB3_07)" .Baking temperature shall be as per APB3_06
52 | Mandatory Appendix: II-TCPH-APB3_13 | 3.3. Pressure and Temperature | 1. Baking details like time and acceptance for bellows is not specified. Kindly provide the same or whether same vacuum handbook, appendix-15 can be followed. | Baking Temp 200 deg C with Appendix-15 requirements shall be followed
53 | Section-B: Technical & management specifications, Scope of Supply and Scope of Work | 4.2 Non-Hardware Items | 1. Whether FE analysis of each components/assembly to be re-done prior to 3D model submission and 2D drawing extraction or whether FE analysis is required only if there is a deviation from the design specified herein. | Not required to Re-FEA prior to model/drawing submission , FE analysis is requirements are mentioned in APB3_10.
54 | Section-B: Technical & management specifications, Scope of Supply and Scope of Work | 4.2 Non-Hardware Items | 1. Please provide the acceptance criteria for the FE analysis of jigs, fixtures and tools as it is not covered under proposed codes. | Jigs Fixture for Factory fabrication will be accepted as per Internal organizational procedure. Transport Fixuture & Handling analysis shall be as per ASME Sec-VIII Div.2 Part-5
55 | Appendix-15 Vacuum Baking | Appendix-15 | 1. Can we outsource Vacuum baking of components and assembly ? Pls confirm. | Yes outsourcing can be done as per sub-contracting requirements of Section-B. Handling of component shall be approved before start of component shifting.
56 | II-TCPH-APB3_13 | II-TCPH-APB3_13 | 1. Please provide probable vendors for the supply of bellows. | Bidder shall explore as per tender requirements. The name of sub-contractor for bellows manufacturing shall be proposed in the part-1 Bid (technical) along with the document showing complience to qualification requirement ( clause 9.1 of section-B ) for the bellows and the sub-contractor will be evaluated as a part of technical bid.
57 | Section-B: Technical & management specifications, Scope of Supply and Scope of Work | Table 6 Technical Requirements | 1. Since the manufacturing is as per ASME Sec.VIII Div.2, the temporary joints can be made on the component and which can be subsequently removed by grinding followed by LPE, whether these temporary joints to weld jigs and fixtures for various manufacturing activities like distortion control, lifting and handling are permitted? | Temp attachment of vacuum side may be accepted with prior approval of I-I on the basis of justified requirement.
58 | Section-B: Technical & management specifications, Scope of Supply and Scope of Work | Table 6 Technical Requirements | If there is a variation between specification and vacuum hand book/applicable Code, which one prevails? | In Case of such variation the same shall be brought to I-I notice for approval.
59 | Drawin-g No. 034280-04-05-C | Part No 602 TCPH Temp. Flange sealing | Material SS304/304L mentioned. Should be viton | Yes, shall be considered as Viton
60 | Section-A (II) | 1.4.3.4 | During the Contract period, to carry out some activities listed in scope of work using the Purchaser’s workstation (especially using ENOVIA/CATIA software), the Contractor needs to deploy his manpower at the Purchaser’s office at the Contractor’s risk and cost. For this, the Purchaser will not provide any facility except office space, workstation and license to work at ITER-India office and will not provide any local hospitality like lodging, transportation, food, etc. Considering concurrent manufacturing scenario, Bidder proposes to perform engineering activities at his design office which is nearby production shops. Drawings will be submitted in PDF format for approval. CATIA Manufacturing model and drawings will be updated in ENOVIA for reference. | Refer Sr. No. 25.
61 | Section-A (II) | 1.7.4.2 | Delivery Schedule: Sr. No. 5 Deliverables of MRR shall be concluded well in advance. | Deleverables are mentioned in MRR Procedure(PA reference No.41)
62 | Section-B | 2 (Table 3) | Reference Documents: We would like to understand the purpose behind including PCR & SRD as a part of reference document package. | It is for refrence to understand the functional requirements.
63 | Section-B | 4.1 | Scope of Supply: We understand that there is no site activity in Bidder's scope. | Site scope is limited to participation and supervision during final acceptance test at site as per 3.3.2 of APB3_11
64 | Section-B | 4.1 Note 4 | All the jigs, fixtures and rigs to be used for Inspection and final acceptance tests at ITER Site shall remain the property of purchaser. Are these items to be supplied by Bidder? Will I-I/IO provide Bill Of Material and manufacturing details? Regarding transport fixture/shippment frame, we understand that it will remain property of purchaser and will be disposed by purchaser. | Bidder shall design a fixture for Inspection & final acceptance if any envisage and supplier shall be responsible for the confirmity of the performance. All jigs Fixtures/Frames/Transport fixture will remain property of Purchaser. It will be disposed by Purchaser if needed.
65 | Section-B | 4.1 | Scope of Supply: We do not have any experience of procuring bellows for ITER projects. Hence, we suggest it to be supplied as FIM. | Bidder shall comply with the full tender scope.
66 | Section-B | 4.2 | Non-Hardware Items We understand that "Non-Hardware Items" means ancillary activities associated with TCPH product supply. | Yes
67 | Section-B | 4.3 | Engineering analysis for manufacturing processes for tolerance requirements as per APB3_10. APB3_10 is only for jigs and fixtures not for manufacturing processes. Therefore, it is understood that none of the manufacturing processes like rolling, bending, welding, machining requires engineering analysis. | The term mentioned in specification is " Engineering Justification" . And not "Engineering Analysis". As per clause " Engineering Justification" is needed to ensure tolernaces.
68 | Section B | 7.1 | TCPH is VQC 1 and SIC 1 component. Significant requirements pertaining to VQC1 is available but similar information specific to SIC1 could not be located in the documents. | Requirements are mentioned in clause 7.0 of section B and also in APB3_01 clause 4.1 .
69 | Section-B | 9.1 | All welding activities shall be performed in-house. We understand that non-critical welding activities pertaining to ancillary jobs shall be allowed to outsource. | All welding activities of TCPH Components shall be peformed in house. For other components, prior approval is needed from I-I.
70 | Section-B | 9.11 | Bidder proposes to make Risk Plan in much simpler way considering all risks having same weightage. | Requirement of tender shall be followed
71 | Appendix-II-TCPH-APB3_01 Manufacturing Requirements | 5 | Bidder proposes to follow standard for unspecified tolerances for welded/fabricated/components made without machining as per ISO 13920 - BF. Unspecified tolerances for machined Components/features as per ISO 2768 - mK. | Agreed, revised drawings shall be supplied along with contract doc
72 | Appendix-II-TCPH-APB3_02 Engineering Drawings | 1 (Drawings) | RT feasibility without 60 mm lip will be confirmed by Bidder. | OK, Drawing requirements shall be followed
73 | Appendix-II-TCPH-APB3_02 Engineering Drawings | 1 (Drawings) | 2 x Dia 6 x 1 Thk Request you to clarify pipe welding & NDE/HLT. | Welding and NDE specification requirement shall be followed for this vacuum boundry joint.
74 | Appendix-II-TCPH-APB3_02 Engineering Drawings | 2 (Drawings) | Can we manufacture 150 mm Thk Shell from plates instead of forging? | Yes, it may be accepted by following technical specifications with prior approval of I-I and validation results of mock-up. A process plan for manufacturing 150mm thk shell from plates shall be submitted along with the technical bid.
75 | Appendix-II-TCPH-APB3_02 Engineering Drawings | 2 (Drawings) | Dwg. No.: 34340 Vertical Plate_03 is not available in the drawing. | Yes it is an error. Refer CATIA model for details. Updated Drawings will be provided at the time of contract award
76 | Appendix-II-TCPH-APB3_02 Engineering Drawings | 8 (Drawings) | We understand that dia 50 f7 Pins (Wherever applicable) to be fillet welded. | It shall be discussed at the time of finalization of manufacturing drawing to comply with functional requirement
77 | Appendix-II-TCPH-APB3_02 Engineering Drawings | 1 (Drawings) | we proposes to introduce note for matching with adjacent part for Hole position for cover – 0.6. | Ageed, revised drawings shall be supplied along with contract doc
78 | Appendix-II-TCPH-APB3_02 Engineering Drawings | 1 (Drawings) | We proposes to relax threaded hole positions on Cryo pump flange from 0.4 to 1 mm. | Not possible to change
79 | Appendix -II TCPH-APB3_03 Welding Requirements | 3.4 | We understand that Welding Procedure Specification (WPS), Procedure Qualification records (PQR) & Welder Performance Qualification (WPQ) shall be as per ASME Sec IX only. Kindly confirm. | Yes
80 | Appendix -II TCPH-APB3_03 Welding Requirements | 3.5.1 | Filler material will be procured as per requirements provided in ASME Sec II C , We Propose Certification as per EN 10204 :2004 Type 3.1 for Chemical properties & Type 2.2 for Mechanical properties. Kindly confirm. | Not possible
81 | Appendix -II TCPH-APB3_03 Welding Requirements | 3.5.1 | We propose Additional Requirements in chemical elements for % Cobalt change from 0.05% Max to 0.2% Max. Kindly confirm. | Not possible
82 | Appendix -II TCPH-APB3_03 Welding Requirements | 4.1 & 4.2 | Filler material will be procured as per ASME Sec II C as mentioned in Clause 3.5.1, Certified material test certificate (CMTR) of each Consumable will be submitted for approval. - We understand that Filler material technical specification need not to be submitted. kindly Confirm. | Specification requirement shall be followed
83 | Appendix -II TCPH-APB3_03 Welding Requirements | 4.5 | Bidder proposes to make Weld data package drawing for seam wise representation for NDE and WEP wise representation for WPS & PQR. Association of weld seams and WEPs will be represented in manufacturing drawings. Kindly confirm. | Specification requirement to be followed. It is up to manufacturer to incorporate as per its system convinience
84 | Appendix -II TCPH-APB3_04 NDE Requirements | 4.1 | In case LPE is required to be performed as per code requirement, the Liquid Dye penetrant tested area shall be subsequently baked at T = 200 ºC for a minimum of 24 hours prior to vacuum leak testing since the TCPH is VQC1A components (RDB3_07). We proposes to eliminate Baking of WEP at 200 ºC post LPE since; residues anyway get burnout during welding. | Acceptable
85 | Appendix -II TCPH-APB3_04 NDE Requirements | 4.1 | The LPE on the welding forming vacuum boundary should be avoided. Otherwise baking is required after the use of LPE We proposes to perform LPE after HLT to avoid the baking. | Not Acceptable, Specification requirement shall be followed
86 | Appendix -II TCPH-APB3_04 NDE Requirements | 4.2 | We understand that Production proof sample (PPS) is required for vacuum boundary weld joints that required 100 % volumetric examination & same is not achievable. Kindly confirm. | Specification requirement shall be followed
87 | Appendix -II TCPH-APB3_04 NDE Requirements |  | Temporary attachment shall not be welded on vacuum surface at any condition. Bidder proposes to weld temporary attachments on vacuum surface with prior approval of I-I to control the application | Refer Sr. No. 57
88 | Appendix -II TCPH-APB3_05 Dimensional Inspection | 3.6 | In addition, these data shall be used to construct a configuration model representing the true geometry of the as-built TCPH. Bidder proposes not to do any short of reverse engineering using cloud of points scanned through laser tracker to generate as-built manufacturing model. Instead, non-conformities would be incorporated in manufacturing model and manufacturing drawings in ENOVIA for reference. | Acceptable
89 | Appendix-II-TCPH-APB 3_06 Vacuum Requirements and Surface Treatment |  | Separate clean area with specific requirements shall be developed. We request to clarify acceptance criteria for the specific requirement of separate clean area. | Dedicated area for stainless steel manufacturing as mentioned in requirement of clean work plan in APB3_06
90 | Appendix-II-TCPH-APB3_07 Leak Testing | 3.2 | Additional accessories like Jigs, seals and temporary closures plates etc. required to perform final site leak testing at site shall be supplied by Bidder along with methodology of fitting and removal. How many sets for testing to be supplied? | Two sets of fixtures (inclusive of fixture used at factory for leak testing in working condition) are to be supplied for final site leak testing.
91 | Appendix-II-TCPH-APB3_07 Leak Testing | 3.3.2 | Global leak testing shall be performed by bidder after completion of final assembly of TCPH with bellows in welded condition. To be performed at bidder's place or at site? | Bidder's Place as mentioned in APB3_11 . The test will again be repeated at site as mentioned in APB_11 clause 3.3.2 of section-B
92 | Appendix-II-TCPH-APB3_07 Leak Testing | 3.2 | Local leak testing shall be carried out by bidder for all welded joints forming a vacuum boundary. Global leak testing shall be performed by bidder after completion of final assembly of TCPH with bellows in welded condition Bidder proposes to perform only global leak test. Please confirm. How many global test required (Inside/Outside) ! kindly clarify. | Specification shall be followed. Global leak test shall cover entire equipments.Detail procedure can be developed and agreed during execution.
93 | Appendix-II-TCPH-APB3_07 Leak Testing |  | Leak testing of welds shall be carried out by probe leak testing (i.e. isolating a section of weld (on the vacuum side only)) in a temporary isolation hood (or suction sup) which is evacuated to at least 3 Pa with a leak detector in series. Bidder proposes 8 Pa with leak detector in series. Bidder understand that for global leak test, requirement for vacuum level is not mandatory. Please confirm. | Specification requriements shall be followed
94 | Appendix-II-TCPH-APB3_07 Leak Testing |  | Helium shall be introduced on the atmospheric pressure side of the weld. A minimum period of observation shall be at least 2 times greater than the response time for Local Leak Test. A minimum period of observation shall be at least 5 times greater than the response time for Global Leak Test. Bidder need clarity on vacuum side and atmospheric side considering TCPH being fitted inside Cryostat boundary. Bidder proposes to perform leak testing irrespective of vacuum or atmospheric side. Bidder proposes for minimum period of observation can be as per code requirement which equal to OR practically more than response time. 5 times greater than response time would be impractical (overdoing). | Specification shall be followed
95 | Appendix-II-TCPH-APB3_09 Labelling, Cleaning, Packing, Shipping and Handling | 5 | The transport fixture designed by the Bidder shall be capable to withstand accelerations up to 5g during transportation from factory to ITER Site. Bidder proposes to design as per EU machinery directives. Designing of transport fixture to withstand acceleration up to 5g may not be practically justified. We understand that transporter should take care during transportation that the package does not have shock more than 5g. Bidder proposes to have transporter’s feedback/inputs (specifically manufacturing inputs) on packing, handling scheme and transport fixture submitted by Bidder. | Transport fixture to be desing by Bidder. Transporting agency will provide feedback/Inputs at the time of finalizing transport fixture design. It is kept as it is in tender.
96 | Appendix-II-TCPH-APB3_12 Material Procurement and Acceptance | 4.1 | Surface roughness: Bidder proposes to procure raw material with 12.5 micron surface roughness instead of 6.3. | Specification Requirements of APB3_12 to be followed
97 |  | 4.3 | Ultrasonic Testing: Bidder proposes to waive off UT of plates below 50mm thickness. | Specification Requirements of APB3_12 to be followed
98 |  | 4.4 | Chemical Composition: Bidder proposes to relax the range for Co from 0.05 to 0.1 and Ta not to be measured. | Specification Requirements of APB3_12 to be followed
99 | Vacuum Handbook | 5.3 | Non metallic inclusions: Bidder proposes to relax inclusion limits up tp 2 for inclusion types A, B, C & D. | Specification Requirements of APB3_12 to be followed
100 |  | 5.4 | Outgassing Test Requirement: Considering long cycle time for setup of outgassing test equipment, Bidder proposes to comply with outgassing test requirement before dispatch rather than before start of manufacturing. Bidder proposes to perform outgassing test at 20ºC and outgassing rate 1 x 10-7 excluding partial outgassing rates for water and hydrogen (hydrogen isotopes/impurities). | Out Gassing is not required as per specification
101 | Appendix-II-TCPH-APB3_14 Mock-up Requirements | 2 | Mock-up shall remain the property of the Bidder after successful completion and acceptance by ITER-India. Can mock-up be used as job item? | It can be accepted in case all the procedures and technical requirement shall followed as applicable to TCPH with prior agreement/approval with I-I for the mock-up plan to ensure full compliance.
102 | Appendix-II-TCPH-APB3_14 Mock-up Requirements | 4 | Welding Documents (WPS, PQR, Welder Qualification Records, Welding Consumables etc.) approved for job will be used for Mock up. Kindly Confirm. | Yes, approved job documents of TCPH can be use for mock-up
103 | Vacuum Handbook | - | Bidder proposes deviation from marking on non vacuum sides consider marking by machine for controlled depth of marking. Bidder also proposes for reference line / trimming line marking by punching at greater pitch for bunch of three punches. | Acceptable
104 | Appendix 17 | - | It is required to understand how outgassing test can be measured. It is not available in the dossier received. | Out Gassing is not required as per specification''