**Annex III b– PRICE SCHEDULE**

**Contract: CAD and Engineering support of In-Vessel and Ex-Vessel diagnostics**

**Reference: IO/20/CFE/10019102/BBE**

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of theServices, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverable | Due date | Amount in EUR |
| D01 | 55. E4 Design work for EWP. DM/CM updates for B1, L1 and L2 of Building 14. Preparing assembly drawings for construction. | T0+ 4 months | *to be added* |
| D02 | 55.E4 Design activities for update of interfaces and CMs on Divertor Cassette, LP#2 , EP#1, UP#1 | T0+ 7 months | *to be added* |
| D03 | 55.G9 Design work update of in vessel design as follow up of analysis outcome. EWP for in-vessel subsystem. Drawings for prototyping and manufacturing of in vessel components. | T0+ 10.5 months | *to be added* |
| D04 | 55.E2 Design work for update of CMs in EP 11 12 Gallery and Diagnostic Building | T0+ 12 months | *to be added* |
| D05 | Summary of activities for the performed work: a report in IDM. | T0+ 12 months | *to be added* |
| ***Total*** | | | ***to be added*** |

The proposed milestone payment plan is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Details | Due date | Amount in EUR |
| M1 | Successful completion of D01, and D02 | TO+ 8 months | *to be added* |
| M2 | Successful completion of D03, D04 and D05 | TO+ 13 months | *to be added* |
| ***Total*** | | | ***to be added*** |

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |