**Annex III b– PRICE SCHEDULE**

**Contract: Magnetic Diagnostics and electrical services preparation and installation**

**Reference: IO/20/CFE/10019154/BBE**

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of theServices, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverable | Due date | Amount in EUR |
| D01 | **Summary report of preparation for steady-state sensors installation** (including links to reports, meeting minutes and technical specifications produced and uploaded in IO IDM) | T0+ 2 months | *to be added* |
| D02 | **Summary report of preparation for feedthroughs Final Design Review** (including links to reports that have been reviewed, independent calculations that have been produced, meeting minutes and records of actions to be performed) | T0+ 4 months | *to be added* |
| D03 | **Summary report of EWP and PLM Handover Packages** (including links to documentation produced and uploaded in IO IDM for three EWP and PLM Handover Packages) | T0+ 6 months | *to be added* |
| D04 | **Requirements Validation and Verification package** (including two updated Design Compliance Matrices with clear substantiation of applicable requirements) | T0+ 8 months | *to be added* |

|  |  |  |  |
| --- | --- | --- | --- |
| D05 | **Report on summary of activities** (including links to actions, residual risks and remaining activities for manufacturing) | T0+ 10 months | *to be added* |
| D06 | **Summary report of steady-state sensors delivery and installation** (including links to SAT reports, meeting minutes and technical documentation produced and uploaded in IO IDM) | T0+ 12 months | *to be added* |
| ***Total*** | | | ***to be added*** |

The proposed milestone payment plan is as follows:

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Details | Due date | Amount in EUR |
| M1 | Successful completion of D01 | TO+ 2 months | *to be added* |
| M2 | Successful completion of D02 | TO+ 4 months | *to be added* |
| M3 | Successful completion of D03 | TO+ 6 months | *to be added* |
| M4 | Successful completion of D04 | TO+ 8 months | *to be added* |
| M5 | Successful completion of D05 | TO+ 10 months | *to be added* |
| M6 | Successful completion of D06 | TO+ 12 months | *to be added* |
| ***Total*** | | | ***to be added*** |