**ANNEX III a – PRICE SCHEDULE**

**Diagnostic Interface Engineering Support**

**Reference: IO/20/CFE/1-19412/LLU**

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of the services, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the services upon the terms and conditions set forth in the Proposal Documents for the following price:

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverables described in the section 6 & 8 of Technical Specifications\_ITER\_D\_3M8FN6\_v1.1 | Due Delivery Dates | Price in EUR |
| D01 | 55.GC, captive supports and studs at L1 level in Bldg 11 (IO) | T0+2 months | *to be added* |
| D02 | 55.C7 captive supports and studs at L1 level in Bldg 11 (IO) | T0+2 months | *to be added* |
| D03 | 55.E4 captive supports at L1 gallery level in Bldg 11 (IO) | T0+4 months | *to be added* |
| D04 | 55.C6 captive supports and studs at L1 level in Bldg 11 (IO) | T0+4 months | *to be added* |
| D05 | 55.C1 captive supports in galleries at L1 level in Bldg 11 (IO) | T0+6 months | *to be added* |
| D06 | 55.C5 and 55.F1 captive supports in galleries at L1 level in Bldg 11 (IO) | T0+6 months | *to be added* |
| D07 | 55.C2 captive supports in galleries at L1 level in Bldg 11 (IO) | T0+6 months | *to be added* |
| D08 | 55.E4 captive supports at B1 gallery level in Bldg 11 (IO) | T0+7 months | *to be added* |
| D09 | 55 Captive supports 55.C4, G8 and studs in Gallery at B1 level in Bldg 11 (IO) | T0+10 months | *to be added* |
| D10 | 55.B8 Neutron Activation System | T0+12 month | *to be added* |
| ***Total Firm and Fixed Price*** | | | ***to be added*** |

\*T0: the date of kick-off Meeting within 1 month after the signature of the contract.

The proposed grouped payment milestone plan is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Milestone Details | Estimated Payment Date | Amount in EUR |
| M1 | IO acceptance of all the deliveries of D1, D2, D3 and D4 | T0\* + 5 months | *to be added* |
| M2 | IO acceptance of all the deliveries of D5, D6, D7 and D8 | T0 + 8 months | *to be added* |
| M3 | IO acceptance of all the deliveries of D9 and D10 | T0 + 13 months | *to be added* |
| ***Total amount to be paid*** | | | ***to be added*** |

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |