***ANNEX III a* – PRICE SCHEDULE**

**Contract: Diagnostic Interface Engineering**

**Reference: IO/*21*/CFE/*10020531*/*INU***

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of the *Supply / Services*, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Supply / Services upon the terms and conditions set forth in the Proposal Documents for the following price:

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverable | Due date | Amount in EUR |
| D01 | Preparation of interface documents (interface sheets, interface control documents) and engineering justification documentation (where interfaces are design drivers) for Equatorial Ports 8 and 17 (with DMS), in preparation for the Port Integration Design Reviews. Upload them in the IDM for review and approval. Prepare relevant presentations for the Design Reviews.  The reviewers of the technical documents need to be coherent with the ITER\_D\_2EXFXU - Sign-Off Authority for Project Documents. | T0 + 2 months | ***to be added*** |
| D02 | Preparation of advanced interface documents (interface sheets, interface control documents) for diagnostic systems in the ports with DMS which are having their Design Reviews in the second quarter of 2021. Upload them in the IDM for review, follow-up and approval. Prepare relevant presentations for the Design Reviews.  The reviewers of the technical documents need to be coherent with the ITER\_D\_2EXFXU - Sign-Off Authority for Project Documents. | T0 + 3 months | ***to be added*** |
| D03 | Preparation of advanced interface documents (interface sheets, interface control documents) for diagnostic systems in the ports with DMS which are having their Design Reviews in the  third quarter of 2021. Upload them in the IDM for review, follow-up and approval. Prepare relevant presentations for the Design Reviews.  The reviewers of the technical documents need to be coherent with the ITER\_D\_2EXFXU - Sign-Off Authority for Project Documents. | T0 + 6 months | ***to be added*** |
| D04 | Preparation of advanced interface documents (interface sheets, interface control documents) for diagnostic and operational systems in the ports with DMS which are having their Design Reviews in the fourth quarter of 2021. Upload them in the IDM for review, follow-up and approval. Prepare relevant presentations for the Design Reviews. The reviewers of the technical documents need to be coherent with the ITER\_D\_2EXFXU - Sign-Off Authority for Project Documents. | T0 + 9 months | ***to be added*** |
| D05 | Preparation of advanced interface documents (interface sheets, interface control documents) for diagnostic and operational systems in the ports with DMS which are having their Design Reviews in the first quarter of 2022. Upload them in the IDM for review, follow-up and approval. Prepare relevant presentations for the Design Reviews. The reviewers of the technical documents need to be coherent with the ITER\_D\_2EXFXU - Sign-Off Authority for Project Documents. | T0 + 12 months | ***to be added*** |
| ***Total*** | | |  |

*T0= kick off meeting date*

The proposed milestone payment plan is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Details | Estimated due date | Amount in EUR |
| *M1* | Successful completion of *D01* | T0 + 3 months | ***to be added*** |
| M2 | Successful completion of *D02* | T0 + 4 months | ***to be added*** |
| M3 | Successful completion of *D03* | T0 + 7 months | ***to be added*** |
| M4 | Successful completion of *D04* | T0 + 10 months | ***to be added*** |
| M5 | Successful completion of *D05* | T0 + 13 months | ***to be added*** |
| ***Total*** | | | ***to be added*** |

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |