## Planning overview
[9 empty] | Total | 68651148.0227
Expected start Contract date | 2021-09-01
Expected End contract date (with options) | 2026-09-01 | [5 empty] | Start Cleaning Service | End Cleaning Service
Building | Responsibility by Sept 2021 | Surface (m2) | Recurrence / month | RFE Date F4E to IO | F4E Taking Over Completion | Duration (months) | Start of construction installation | End of construction installation | Remaining duration from Start Contract Date | Total Units: m2 x month x recurrence
A53 | SIM | 5165 | 1 |  | 2025-12-31 |  | 2017-12-01 | 2021-06-01 |  | 0
B01 | SIM | [8 empty] | 0
B03 | SIM | [8 empty] | 0
B04 | SIM | [8 empty] | 0
B06 | SIM | [8 empty] | 0
B07 | SIM | [8 empty] | 0
B08 | SIM | [8 empty] | 0
B09 | SIM | [8 empty] | 0
B11 B1 | SPC | 3580 | 8.6667 | 2020-03-05 | 2023-10-26 | 59.8333 | 2020-11-01 | 2025-10-01 | 49.7 | 771012.6667
B11 B2 | SPC | 3815 | 8.6667 | 2020-05-29 | 2023-10-26 | 41.5 | 2018-06-01 | 2025-12-01 | 51.7333 | 855238.2222
B11 B2M | SPC | 1108 | 8.6667 | 2020-05-29 | 2023-10-26 | 41.5 | 2020-05-01 | 2024-08-01 | 35.5 | 170447.3333
B11 L1 | SPC | 4000 | 8.6667 | 2020-10-09 | 2023-10-26 | 37.0667 | 2021-01-01 | 2026-09-01 | 60.8667 | 1055022.2222
B11 L2 | SPC | 2850 | 8.6667 | 2020-12-09 | 2023-10-26 | 35.0333 | 2021-04-01 | 2026-03-01 | 54.7333 | 675956.6667
B11 L3 | SPC | 4698 | 8.6667 | 2021-03-31 | 2023-10-26 | 31.3 | 2021-04-01 | 2026-01-01 | 52.7667 | 1074223.8
B11 L4 | SPC | 1400 | 8.6667 | 2021-01-29 | 2023-10-26 | 33.3333 | 2021-04-01 | 2025-11-01 | 50.7333 | 307782.2222
B11 L5 | SPC | 1000 | 8.6667 | 2021-01-29 | 2023-10-26 | 33.3333 | 2021-06-01 | 2024-06-01 | 33.4667 | 145022.2222
B11 PIT | SPC | 2300 | 21.6667 | 2020-03-28 | 2023-10-26 | 43.5667 | 2018-10-01 | 2026-02-01 | 53.8 | 1340516.6667
B11 R1 | SPC | 1000 | 8.6667 | 2020-10-02 | 2023-10-26 | 37.3 | 2021-06-01 | 2024-02-01 | 29.4333 | 127544.4444
B11 Building and common areas | ?? |  | 8.6667
B13 Hall area (without offices) | SPC | 5156 | 21.6667 | 2017-09-15 | 2023-10-26 | 74.4 | - | 2025-10-01 | 49.7 | 2776076.3333
B13 offices | SIM
B14 B1 | SPC | 4327 | 8.6667 | 2021-07-15 | 2026-02-10 | 55.7 | 2021-07-01 | 2024-03-01 | 30.4 | 570010.1333
B14 B2 | SPC | 4583 | 8.6667 | 2021-07-15 | 2026-02-10 | 55.7 | 2021-02-01 | 2024-02-01 | 29.4333 | 584536.1889
B14 L1 | SPC | 4698 | 8.6667 | 2021-07-15 | 2026-02-10 | 55.7 | 2021-07-01 | 2024-09-01 | 36.5333 | 743745.6
B14 L2 | SPC | 4698 | 8.6667 | 2022-10-20 | 2026-02-10 |  | 2022-06-01 | 2024-02-01 | 20.3333 | 413946
B14 L3 | SPC | 4698 | 8.6667 | 2023-02-01 | 2026-02-10 | 12.1667 | 2023-02-01 | 2024-02-01 | 12.1667 | 247689
B14 L4 | SPC | 1400 | 8.6667 | 2023-07-21 | 2026-02-10 | 10.1667 | 2023-06-01 | 2024-04-01 | 10.1667 | 61677.7778
B14 L5 | SPC | 1017 | 1 | 2023-11-02 | 2026-02-10 | 15.2667 | 2023-07-01 | 2024-10-01 | 15.2667 | 7763.1
B14 R1 | SPC | 1000 | 1 | 2023-10-09 | 2026-02-10 | 18.2667 | 2023-10-01 | 2025-04-01 | 18.2667 | 9133.3333
B15 | SPC | 7261 | 1 | 2022-01-28 | 2022-12-23 | 76.0667 | 2020-04-01 | 2026-07-01 | 76.0667 | 276160.0333
B16 | SIM |  |  |  |  | 0 |  |  |  | 0
B17 (East and West Annexes) | SIM |  |  | 2017-06-26 | 2020-10-06 | 39.9333 |  |  |  | 0
B17 Main Hall | SPC | 2513 | 21.6667 | 2017-06-26 | 2020-10-06 | 39.9333 |  | 2026-09-01 | 60.8667 | 3314088.5556
B19 | Pro Rata |  |  |  |  | 0 |  |  |  | 0
B21 | Pro Rata |  |  | 2028-11-21 | 2028-12-19 | 0.93333 |  |  |  | 0
B22 | SIM |  |  |  |  | 0 |  | 2021-01-01 |  | 0
B23 | Pro Rata |  |  | 2027-02-15 | 2027-09-09 | 6.8667 |  |  |  | 0
B24 | Pro Rata |  |  | 2027-03-12 | 2027-10-06 | 6.9333 |  |  |  | 0
B25 | ?? |  |  |  |  | 0 |  |  |  | 0
B30 | TB12 |  |  |  |  | 0 |  |  |  | 0
B31 | TB12 |  |  |  |  | 0 |  |  |  | 0
B32 | SPC | 2300 | 8.6667 | 2017-12-22 | 2019-03-15 | 14.9333 |  | 2025-12-01 | 51.7333 | 515608.8889
B33 | SPC | 1970 | 8.6667 | 2017-12-22 | 2019-03-15 | 14.9333 |  | 2023-09-01 | 24.3333 | 207725.5556
B34 | TB12 | 1000 | 1 | 2023-05-24 | 2023-11-15 | 6.1333 | 2023-07-01 | 2024-01-01 | 6.1333 | 3066.6667
B36 | SIM |  |  | 2019-01-25 | 2019-10-21 | 8.9667 |  |  |  | 0
B37 | TB12 | 1000 | 1 | 2023-07-27 | 2024-04-03 | 2 | 2024-02-01 | 2024-04-01 | 2 | 1000
B38 | SPC | 580 | 4.3333 | 2017-12-22 | 2019-03-15 | 14.9333 | 2019-03-01 | 2022-10-01 | 13.1667 | 16546.1111
B42 | ?? |  |  | 2029-11-15 | 2030-01-28 | 2.4667 |  |  |  | 0
B43 | ?? |  |  | 2029-11-15 | 2030-01-28 | 2.4667 |  |  |  | 0
B44 | TB13 | 1000 | 1 | 2023-06-16 | 2023-12-20 | 24.3333 | 2022-01-01 | 2024-01-01 | 24.3333 | 12166.6667
B45 | TB13 | 1000 | 1 | 2023-06-16 | 2023-12-20 | 19.3333 | 2023-06-01 | 2025-01-01 | 19.3333 | 9666.6667
B46 | TB13 | 1000 | 1 | 2023-06-16 | 2023-12-20 | 7.1333 | 2023-06-01 | 2024-01-01 | 7.1333 | 3566.6667
B47 | TB13 | 1000 | 1 | 2023-06-16 | 2023-12-20 | 7.1333 | 2023-06-01 | 2024-01-01 | 7.1333 | 3566.6667
B51 | SPC | 1170 | 21.6667 | 2021-03-08 | 2021-03-31 | 0.76667 | - | 2021-12-01 | 3.0333 | 38447.5
B52 | SPC | 1410 | 21.6667 | 2021-03-08 | 2021-03-31 | 0.76667 | - | 2023-09-01 | 24.3333 | 371691.6667
B54 | SIM |  |  |  |  | 0 |  |  |  | 0
B55 | SIM |  |  |  |  | 0 |  |  |  | 0
B55.1 | SIM |  |  |  |  | 0 |  |  |  | 0
B55.2 | SPC | 5910 | 1 |  | 2026-09-01 | 1542.2 |  | 2026-09-01 | 60.8667 | 359722
B56 | SIM |  |  |  |  | 0 |  |  |  | 0
B57 | TB13 |  |  | 2030-09-16 | 2030-11-20 | 2.1667 |  |  |  | 0
B58 | TB13 |  |  | 2030-09-16 | 2030-11-20 | 2.1667 |  |  |  | 0
B59 | TB13 |  |  | 2030-01-14 | 2030-03-18 | 2.1 |  |  |  | 0
B60 | TB13 |  |  | 2030-01-14 | 2030-03-18 | 2.1 |  |  |  | 0
B61 | SIM | 2312 | 1 | 2018-03-08 | 2020-12-15 | 33.7667 | - | 2021-01-01 |  | 0
B62 | SIM |  |  |  | 2021-08-31 | 1481.3 |  |  |  | 0
B64 | SPC | 1000 | 21.6667 | 2018-04-25 | 2018-12-21 | 8 | - | 2022-12-01 | 15.2 | 164666.6667
B66 | SIM |  |  |  |  | 0 |  |  |  | 0
B67 | SPC | 1000 | 21.6667 | 2018-04-25 | 2018-12-21 | 8 |  | 2022-12-01 | 15.2 | 164666.6667
B68A | SPC | 1000 | 21.6667 | 2018-04-25 | 2018-12-21 | 8 |  | 2022-12-01 | 15.2 | 164666.6667
B68B | TB06 | 1000 | 1 | 2021-01-29 | 2021-03-22 | 15.2 | 2021-09-01 | 2022-12-01 | 15.2 | 7600
B69 | SPC | 1000 | 21.6667 |  |  | 0 |  | 2022-12-01 | 15.2 | 164666.6667
B71 North | TB12 | 1000 | 1 | 2022-06-30 | 2023-07-12 | 19.3 | 2022-06-01 | 2024-01-01 | 19.3 | 9650
B71 South | ?? |  |  | 2027-05-05 | 2028-03-28 | 19.3 | 2022-06-01 | 2024-01-01 | 19.3 | 0
B72 | SIM |  |  |  |  | 0 |  |  |  | 0
B73.1 | SPC | 500 | 8.6667 |  | 2026-09-01 | 1542.2 |  | 2026-09-01 | 60.8667 | 131877.7778
B73.2 | TAC2 | 3663.18 | 1 |  | 2026-09-01 | 1542.2 |  | 2026-09-01 | 60.8667 | 222965.556
B74 B1 | SPC | 1298 | 8.6667 | 2019-02-28 | 2022-06-03 | 39.7 | 2020-04-01 | 2024-03-01 | 30.4 | 170989.8667
B74 B2 | SPC | 1298 | 8.6667 | 2018-12-05 | 2022-06-03 | 42.5333 | 2018-06-01 | 2024-09-01 | 36.5333 | 205487.8222
B74 L1 | SPC | 1298 | 8.6667 | 2019-04-19 | 2022-06-03 | 38.0333 | 2019-01-01 | 2024-07-01 | 34.4667 | 193863.5111
B74 L2 | SPC | 1298 | 8.6667 | 2019-06-18 | 2022-06-03 | 36.0333 | 2021-03-01 | 2024-04-01 | 31.4333 | 176802.0222
B74 L3 | SPC | 1298 | 8.6667 | 2019-09-23 | 2022-06-03 | 32.8 | 2021-03-01 | 2024-04-01 | 31.4333 | 176802.0222
B74 L4 | SPC | 678 | 8.6667 | 2020-10-19 | 2022-06-03 | 19.7333 | 2021-04-01 | 2023-01-01 | 16.2333 | 47693.5333
B74 L5 | SPC | 105 | 8.6667 | 2020-10-19 | 2022-06-03 | 19.7333 | 2021-04-01 | 2022-11-01 | 14.2 | 6461
B74 R1 | SPC | 1000 | 1 | 2020-10-19 | 2022-06-03 | 19.7333 | 2021-05-01 | 2024-02-01 | 29.4333 | 14716.6667
B75 | TB12 | 1000 | 1 | 2022-04-26 | 2023-03-15 | 20.3 | 2022-04-01 | 2023-12-01 | 20.3 | 10150
B76 | SIM |  |  |  |  | 0 |  |  |  | 0
B77 | SIM |  |  |  |  | 0 |  |  |  | 0
B78 | SIM |  |  |  |  | 0 |  |  |  | 0
B79 | SIM |  |  |  |  | 0 |  |  |  | 0
B80.1 | SIM |  |  |  |  | 0 |  |  |  | 0
B80.2 | SIM |  |  |  |  | 0 |  |  |  | 0
B81 | SIM |  |  |  |  | 0 |  |  |  | 0
B82 | SIM |  |  |  |  | 0 |  |  |  | 0
B83 | SIM |  |  |  |  | 0 |  |  |  | 0
B86 | SIM |  |  |  |  | 0 |  |  |  | 0
B87 | SIM |  |  |  |  | 0 |  |  |  | 0
B88 | SIM |  |  |  |  | 0 |  |  |  | 0
B89 | SIM |  |  |  |  | 0 |  |  |  | 0
B89.1 | SIM |  |  |  |  | 0 |  |  |  | 0
B89.2 | SIM |  |  |  |  | 0 |  |  |  | 0
B89.3 | SIM |  |  |  |  | 0 |  |  |  | 0
B91 | SIM |  |  |  |  | 0 |  |  |  | 0
B92 | SIM |  |  |  |  | 0 |  |  |  | 0
B93 | SIM |  |  |  |  | 0 |  |  |  | 0
B94 | SIM |  |  |  |  | 0 |  |  |  | 0
B95 | SIM |  |  |  |  | 0 |  |  |  | 0
B96 | SIM |  |  |  |  | 0 |  |  |  | 0
B97 | SIM |  |  |  |  | 0 |  |  |  | 0
B98.1 | SIM |  |  |  |  | 0 |  |  |  | 0
B98.2 | SIM |  |  |  |  | 0 |  |  |  | 0
C3 | SIM |  |  |  |  | 0 |  |  |  | 0
C4 | SIM |  |  |  |  | 0 |  |  |  | 0
C5 | SIM |  |  |  |  | 0 |  |  |  | 0
LC01 | SIM | 1000 | 1 | 2023-01-24 | 2023-02-28 | 1.1667 |  |  |  | 0
LC02 | SIM | 1000 | 1 | 2021-08-06 | 2021-09-10 | 1.1667 |  |  |  | 0
LC03 | SIM | 1000 | 1 | 2020-10-30 | 2020-12-14 | 1.5 |  |  |  | 0
LC04 | SIM | 1000 | 1 | 2022-08-12 | 2022-09-19 | 1.2667 |  |  |  | 0
LC05 | SIM |  |  | 2020-07-21 | 2020-10-15 | 2.8667 |  |  |  | 0
LC06 | SIM | 1000 | 1 | 2020-11-03 | 2020-12-02 | 0.96667 |  |  |  | 0
LC08 | SIM | 1000 | 1 | 2022-01-05 | 2022-02-09 | 1.1667 |  |  |  | 0
LC09 | SIM | 1000 | 1 | 2023-04-06 | 2023-05-09 | 1.1 |  |  |  | 0
LC10 | SIM | 1000 | 1 | 2020-09-30 | 2020-11-30 | 2.0333 |  |  |  | 0
LC11 | SIM |  |  | 2019-01-22 | 2019-01-22 | 0 |  |  |  | 0
LC13 | SIM | 1000 | 1 | 2025-04-25 | 2025-06-02 | 1.2667 |  |  |  | 0
LC14 | SIM |  |  | 2020-09-18 | 2020-10-15 | 0.9 |  |  |  | 0
LC15 | SIM | 1000 | 1 | 2022-08-30 | 2022-10-04 | 1.1667 |  |  |  | 0
LC16 | SIM | 1000 | 1 | 2022-08-30 | 2022-10-04 | 1.1667 |  |  |  | 0
MV01 | SIM | 1000 | 1 | 2020-10-30 | 2020-12-04 | 1.1667 |  |  |  | 0
MV02 | SIM | 1000 | 1 | 2020-09-11 | 2020-10-30 | 1.6333 |  |  |  | 0
MV03 | SIM | 1000 | 1 | 2020-09-18 | 2020-10-30 | 1.4 |  |  |  | 0
MV04 | SIM | 1000 | 1 | 2022-08-24 | 2022-08-30 | 0.2 |  |  |  | 0
MV05 | SIM | 1000 | 1 | 2022-08-03 | 2022-08-10 | 0.23333 |  |  |  | 0
MV06 | SIM | 1000 | 1 | 2022-06-23 | 2022-06-30 | 0.23333 |  |  |  | 0
Floor cleaning WS01 | SPC | 170000 | 1 |  | 2026-09-01 |  |  | 2026-09-01 | 60.8667 | 10347333.3333
WS01 : Vertical Cleaning team | SPC | 74000 | 1 |  | 2026-09-01 |  |  | 2026-09-01 | 60.8667 | 4504133.3333
B11 PIT: Cleaning CR Base in B2 and B1 levels | SPC | 2500 | 21.6667 | 2020-03-28 | 2023-10-26 | 43.5667 | 2018-10-01 | 2026-02-01 | 53.8 | 1457083.3333
Cleaning of vertical pumps | SPC | 64000 | 1 |  | 2026-09-01 |  |  | 2026-09-01 | 60.8667 | 3895466.6667
Stairs cleaning | SPC | 50000 | 1 |  | 2026-09-01 |  |  | 2026-09-01 | 60.8667 | 3043333.3333
Waste evacuation (Tokamak Complex) | SPC | 2500 | 1 |  | 2026-09-01 |  |  | 2026-09-01 | 60.8667 | 152166.6667
Toilet areas | SPC | 200000 | 1 |  | 2026-09-01 |  |  | 2026-09-01 | 60.8667 | 12173333.3333
Common Smoking areas / trash cans | SPC | 49560 | 1 |  | 2026-09-01 |  |  | 2026-09-01 | 60.9 | 3018204
Outside areas | SPC | 80000 | 1 |  | 2026-09-01 |  |  | 2026-09-01 | 60.8667 | 4869333.3333
Miscellaneous | SPC | 100000 | 1 |  | 2026-09-01 |  |  | 2026-09-01 | 60.8667 | 6086666.6667
Z1.1 | SIM | [8 empty] | 0
Z1.2 | SIM | [8 empty] | 0
Z2.1 | SIM | [8 empty] | 0
Z3.1 | SIM | [8 empty] | 0
Z3.2 | SIM | [8 empty] | 0
Note on A146: Chartron Sylvain: 17 currently expected 34 including pro rata ones