Annex III b – PRICE SCHEDULE

Contract: 	Project Integration of 55 BT Neutron Facility and Neutron diagnostics

Reference:	 IO/22/CFE/10023184/BBE

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of the Services, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price:

| D# | Deliverables as described in the Technical Specifications ITER_D_ 7DYYLV v1.1 dated 07 March 2022 | Deliverable due date | Payment amount in EUR |
| --- | --- | --- | --- |
| D1 | - Provide documentation for the construction of Neutron Storage Area in the zone Z4.2 GBS, cost estimation of containers and work/time plan, electrical services, safety ASN documentation update in agreement with SRO for the Group 1 Nuclear sources and detectors. - Documentation and licenses procedures regarding the transportation from the DA to IO sites and to storage at IO site of neutron detectors with fissile material and low yield radioactive sources | T0* + 3 month | to be added |
| D2 | - Contribute to the Preliminary Design Phase of the 55BV In Vessel Neutron calibration project: Identify and complete Interfaces documentation; organize and coordinate the safety records and provide safety documentation update; - Support the progress of the Preliminary design and integration with the other PBS (Assembly, Vacuum Vessel, Remote handling, Lower Ports, Blankets) | T0* + 6 months | to be added |
| D3 | - Support neutron transport calculations, investigations on the performance and shielding features of neutron/gamma diagnostics system of ITER. - Follow up of Documentation and licensing procedures regarding the transportation from the DA to IO sites and to storage at IO site of neutron detectors with fissile material and low yield radioactive sources | T0+ 9 months | to be added |
| D4 | - Provision of specifications/requirements for storing the Group 2 Nuclear sources and detectors in the Port Integration Facility (PIF). - Update of the safety records and safety documentation in agreement with SRO; - Support the progress of the integration with the other PBS55 diagnostics in PIF | T0+ 12 months | to be added |
| Total (EUR) |  |  | to be added |

*TO: Kick off Meeting date:  it should take place within a month after signature of the contract by both parties

The proposed milestone payment plan is as follows:

| M# | Details | Due date | Amount in EUR |
| --- | --- | --- | --- |
| M1 | Successful completion of D1 | T0*+ 4 months | to be added |
| M2 | Successful completion of D2 | T0+ 7 months | to be added |
| M3 | Successful completion of D3 | T0+10 months | to be added |
| M4 | Successful completion of D4 | T0+13 months | to be added |
| Total |  |  | to be added |

| Signature: |  | COMPANY STAMP |
| --- | --- | --- |
| Name: |  |  |
| Position: |  |  |
| Tel: |  |  |
| Email: |  |  |
| Date: |  |  |

*TO: Kick Off Meeting date:  it should take place within a month after signature of the contract by both parties