Annex III b – PRICE SCHEDULE

Contract: 	Thermal hydraulics design of Diagnostic Port Plugs components

Reference:	 IO/22/CFE/10023595/CPT

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of the Services, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price

| D# | Deliverable description (Technical Specifications ref ITER_D_ 7PNU4J v1.1) | Due date | Amount in EUR |
| --- | --- | --- | --- |
| D01 | Cooling design (CAD models) and Supporting analyses results justifying the performance of DSM#01 – EQ#17. Thermal hydraulics report using template provided by IO. | T0* + 1 months | to be added |
| D02 | Cooling design (CAD models) and Supporting analyses results justifying the performance of DSM#02 – EQ#17. Thermal hydraulics report using template provided by IO. | T0 + 2 months | to be added |
| D03 | Cooling design (CAD models) and Supporting analyses results justifying the performance of DSM#03 – EQ#17. Thermal hydraulics report using template provided by IO. | T0 + 3 months | to be added |
| D04 | Cooling design (CAD models) and Supporting analyses results justifying the performance of DFW#1. Thermal hydraulics report using template provided by IO. | T0 + 4 months | to be added |
| D05 | Cooling design (CAD models) and Supporting analyses results justifying the performance of DFW#2. Thermal hydraulics report using template provided by IO. | T0 + 5 months | to be added |
| D06 | Cooling design (CAD models) and Supporting analyses results justifying the performance of DFW#3. Thermal hydraulics report using template provided by IO. | T0 + 6 months | to be added |
| D07 | Cooling design (CAD models) and Supporting analyses results justifying the performance of DFW#4. Thermal hydraulics report using template provided by IO. | T0 + 7 months | to be added |
| D08 | Cooling design (CAD models) and Supporting analyses results justifying the performance of DFW#5. Thermal hydraulics report using template provided by IO. | T0 + 8 months | to be added |
| D09 | Cooling design (CAD models) and Supporting analyses results justifying the performance of DFW#6. Thermal hydraulics report using template provided by IO. | T0 + 9 months | to be added |
| D10 | Advance progress report describing the customizable (macro, script…) hydraulic dynamic model of the whole Port Plug including DSMs, DFWs, diagnostics and PP structure cooling circuits. | T0 + 10 months | to be added |
| D11 | Advance progress report describing the customizable (macro, script…) hydraulic dynamic model of the whole Port Plug including DSMs, DFWs, diagnostics and PP structure cooling circuits. | T0 + 11 months | to be added |
| D12 | Final report describing the customizable (macro, script…) hydraulic dynamic model of the whole Port Plug including DSMs, DFWs, diagnostics and PP structure cooling circuits. | T0 + 12 months | to be added |
|  | Total |  | to be added |

*T0: date of KoM to take place within one month after signature of the Contract by both parties

The proposed milestone payment plan is as follows:

| M# | Details | Due date | Amount in EUR |
| --- | --- | --- | --- |
| M1 | Successful completion of D01 | T0* + 2 months | to be added |
| M2 | Successful completion of D02 | T0 + 3 months | to be added |
| M3 | Successful completion of D03 | T0 + 4 months | to be added |
| M4 | Successful completion of D04 | T0 + 5 months | to be added |
| M5 | Successful completion of D05 | T0 + 6 months | to be added |
| M6 | Successful completion of D06 | T0 + 7 months | to be added |
| M7 | Successful completion of D07 | T0 + 8 months | to be added |
| M8 | Successful completion of D08 | T0 + 9 months | to be added |
| M9 | Successful completion of D09 | T0 + 10 months | to be added |
| M10 | Successful completion of D10 | T0 + 11 months | to be added |
| M11 | Successful completion of D11 | T0 + 12 months | to be added |
| M12 | Successful completion of D12 | T0 + 13 months | to be added |
| Total |  |  | to be added |

* T0: date of KoM to take place within one month after signature of the Contract by both parties

| Signature: |  | COMPANY STAMP |
| --- | --- | --- |
| Name: |  |  |
| Position: |  |  |
| Tel: |  |  |
| Email: |  |  |
| Date: |  |  |