**ANNEX III– PRICE SCHEDULE**

**Contract: Service Contract for Electrical Engineering support for diagnostic port integration**

**Reference: IO/20/CFE/10019163/KJT**

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of the Services, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price:

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverables as described in Chapter 7 of the technical Specifications ITER\_D\_3DV3AT dated 13th May 2020 | Due date | Amount in EUR |
| D01 | Outcome of integration of electric services in equatorial ports  - List of cable needs and cable diagrams  - Detailed layout of electrical services  - BOM of electrical services  - Ex-vessel cable arrangement | T0\* + 6 Months | to be added |
| D02 | Outcome of integration of electric services in Upper ports  - List of cable needs and cable diagrams  - Detailed layout of electrical services  - BOM of electrical services  - Ex-vessel cable arrangement. | T0\* + 11 Months | to be added |
| D03 | Collection of LEVI components needs/requirements from Port  integration and tenants  - Cable types, number of cables, connectors, LEF,  - Signal characteristics  - others | T0\* + 8 Months | to be added |
| D04 | Technical specification of LEVI components specified in  section 5.4 | T0\* + 7 Months | to be added |
| D05 | Summary of the technical support: list of document reviews, minutes of technical meetings, etc. | T0\* + 12 Months | to be added |
| **Total** | | | **to be added** |

T0\* is the signature date of the contract

The proposed milestone payment plan is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Details | Due date | Amount in EUR |
| M1 | Successful completion of D 01 | T0\* + 6 Months | to be added |
| M2 | Successful completion of D 04 | T0\* + 7 Months | to be added |
| M3 | Successful completion of D 03 | T0\* + 8 Months | to be added |
| M4 | Successful completion of D 02 | T0\* + 11 Months | to be added |
| M5 | Successful completion of D 05 | T0\* + 12 Months | to be added |
| **Total** | | | ***to be added*** |

T0\* is the signature date of the contract

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |