**Annex III b– PRICE SCHEDULE**

**Contract: VUV and XRay diagnostics management**

**Reference: IO/21/CFE/10022217/CPT**

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of theServices, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverable description as defined in section 8 in Technical Specifications ref ITER\_D\_ 64A4VK v1.1) | Due date | Amount in EUR |
| D#01 | Quality Plan | T0\* + 1 months | *to be added* |
| D#02 | Preliminary Design Review for the XRCS Survey – 55.ED / I&C | T0 + 4 months | *to be added* |
| D#03 | Preliminary Design Review for the XRCS Edge – 55.EI | T0 + 5 months | *to be added* |
| D#04 | Manufacturing Readiness Review for the VUV Core Survey – 55.E3 | T0 + 7 months | *to be added* |
| D#05 | Final Design Review for the VUV Divertor – 55.EG | T0 + 9 months | *to be added* |
| D#06 | Final Design Review for the XRCS Survey– 55.ED | T0 + 10 months | *to be added* |
| D#07 | Final summary report | T0 + 12 months | *to be added* |
|  | **Total** |  | ***to be added*** |

\**T0: Kick off Meeting date, to take place within a month after the signature of the contract by both parties*

The proposed milestone payment plan is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Details | Due date | Amount in EUR |
| M1 | Successful completion of D#01 | T0\*+ 2 months | *to be added* |
| M2 | Successful completion of D#02 | T0+ 5 months | *to be added* |
| M3 | Successful completion of D#03 | T0+ 6 months | *to be added* |
| M4 | Successful completion of D#04 | T0+ 8 months | *to be added* |
| M5 | Successful completion of D#05 | T0+ 10 months | *to be added* |
| M6 | Successful completion of D#06 | T0+ 11 months | *to be added* |
| M7 | Successful completion of D#07 | T0+ 13 months | *to be added* |
| ***Total*** | | | ***to be added*** |

*\*T0: Kick off Meeting date, to take place within a month after the signature of the contract by both parties*

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |