**Annex III b– PRICE SCHEDULE**

**Contract: Common Engineering Support for Equatorial Port #08 and #17 with Disruption Mitigation System**

**Reference: IO/21/CFE/10022615/KJT**

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of theServices, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverable description as defined in section 8 in Technical Specifications ref ITER\_D\_6CVTMF v1.1 | Due date | Amount in EUR |
| D01 | Preparation of interface documents (interface sheets, interface control documents) and engineering justification documentation (where  interfaces are design drivers) for Equatorial Ports with DMS. Upload them in the IDM for review and approval. Prepare and follow up Input Package (List of Documents) for Design Reviews of Equatorial Ports with DMS. Prepare EWP and CWP related documents. Prepare relevant presentations for the Design Reviews to be held in 2022 Q1 and Q2. | T0\* + 4 months | *to be added* |
| D02 | Preparation of advanced interface documents (interface sheets, interface control documents) for Equatorial Ports with DMS in preparation for the Port Integration Design Reviews to be held in  2022 Q3 and Q4. Prepare relevant presentations for the Design Reviews. Prepare assembly documentation (scope document, storage and preservation document, list of the drawings, etc) as per request.  Prepare ORE calculation technical notes for Equatorial Port #08 ports Page 7 of 9 with DMS. Contribute into creation of CPDs for Equatorial Ports with DMS. Upload them in the IDM for review, follow-up and approval. | T0 + 8 months | *to be added* |
| D03 | Prepare minutes of the progress meetings with DMS and diagnostic tenants and upload them in IDM. Update documents from Design Review input package as per reviewer’s comment. Prepare ORE calculation technical notes for Equatorial Port #17 with DMS.  Preparation of advanced interface documents (interface sheets, interface control documents) for Equatorial Ports with DMS for the Port Integration Design Reviews to be held in 2023 Q1. Prepare  CPDs for Equatorial Ports with DMS. Upload them in IDM for review and approval. | T0 + 12 months | *to be added* |
|  | **Total** |  | ***to be added*** |

\**T*0*: is the date of the Contract signature*

The proposed milestone payment plan is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Details | Estimated due date | Amount in EUR |
| M1 | Successful completion of D01 | T0\* + 5 months | *to be added* |
| M2 | Successful completion of D02 | T0 + 9 months | *to be added* |
| M3 | Successful completion of D03 | T0 + 13 months | *to be added* |
| ***Total*** | | | ***to be added*** |

\**T*0*: is the date of the Contract signature*

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |