**Annex III b– PRICE SCHEDULE**

**Contract: Diagnostic Expert Support for 55.G8 Erosion Deposition Monitor**

**Reference: IO/22/CFE/10023295/CPT**

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of theServices, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverable summary (extensive description in Technical Specifications ref ITER\_D\_ 7H3PRG v1.0) | Due date | Amount in EUR |
| D01 | Supervise 55.G8 mechanical design and engineering contract TO#01 | T0\* + 2 months | *to be added* |
| D02 | Supervise 55.G8 mechanical design and engineering contract TO#01 | T0 + 4 months | *to be added* |
| D03 | Supervise 55.G8 mechanical design and engineering contract TO#01 | T0 + 6 months | *to be added* |
| D04 | Supervise 55.G8 mechanical design and engineering contract TO#01 | T0 + 8 months | *to be added* |
| D05 | Supervise 55.G8 mechanical design and engineering contract TO#02 | T0 + 10 months | *to be added* |
| D06 | Supervise 55.G8 mechanical design and engineering contract TO#02 | T0 + 12 months | *to be added* |
|  | **Total** |  | ***to be added*** |

\**T0: Kick off Meeting date, to take place within a month after the signature of the contract by both parties*

The proposed milestone payment plan is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Details | Due date | Amount in EUR |
| M1 | Successful completion of D01 | T0\*+ 3 months | *to be added* |
| M2 | Successful completion of D02 | T0+ 5 months | *to be added* |
| M3 | Successful completion of D03 | T0+ 7 months | *to be added* |
| M4 | Successful completion of D04 | T0+ 9 months | *to be added* |
| M5 | Successful completion of D05 | T0 + 11 months | *to be added* |
| M6 | Successful completion of D06 | T0 + 13 months | *to be added* |
| ***Total*** | | | ***to be added*** |

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |

*\*T0: Kick off Meeting date, to take place within a month after the signature of the contract by both parties*